## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Procurment
Work with GM @ North location location to identiy number of tablets needed. |  |  |  | 0 | bar: WEEK 1 M
Work with GM @ Downtown to identify number of tablets needed. |  |  |  | 0 | bar: WEEK 1 M
Determine if we will purchase and store backup tablets for emergencies |  |  |  | 0 | bar: WEEK 1 M
Assess available tablet options and specs from the supplier that meet requirements. |  |  |  | 0 | bar: WEEK 1 M
Create contract and statements of work for tablet vendor |  |  |  | 2 | bar: WEEK 1 T to WEEK 1 W
Buy and receive the correct amount of tablets | Due to force majeure storm we need to wait(2 more weeks), or use an alternative supplier(5 days) |  |  | 10 | bar: WEEK 1 W to WEEK 3 T
Milestone: Prepare for rollout
Connect marketing team with Supplier for branding and digital menu design |  |  |  | 0 | bar: WEEK 1 W
Work with Executive Chef on possible menu revamp |  |  |  | 10 | Carter | bar: WEEK 1 W to WEEK 3 T
Add featured menu items and coupon values to tablets |  |  |  | 1 | Deanna, Carter, Marketing | bar: WEEK 3 T
Work with tablet supplier to identify any common issues |  |  |  | 2 | Peta | bar: WEEK 1 R to WEEK 2 F
Develop internal policy and troubleshooting guides for the tablet rollout |  |  |  | 3 | Peta | bar: WEEK 1 R to WEEK 2 F
Assess work required to ensure tablets integrate with existing hardware |  |  |  | 3 | bar: WEEK 1 F to WEEK 2 F
Milestone: Training
Develop a training program and rollout guide |  |  |  | 7 | Peta/Seydou | bar: WEEK 1 R to WEEK 2 F
Pre-training meeting to introduce tablets and changes |  |  |  | 1 | Seydou | bar: WEEK 1 F; WEEK 2 W to WEEK 2 F
Cheif Tech will train GMs and key staff on tablets and end of shift security measures |  |  |  | 2 | Seydou
Work with GMs to coordinate, schedule, and hold meetings to discuss rollout and report questions/concerns |  |  |  | 7 | bar: WEEK 2 M to WEEK 4 T
Milestone: Installation
Identify bar section tables that need to be wired properly by electrician |  |  |  | 0 | bar: WEEK 3 T
Install one tablet to ensure proper installation and to identify any potential issues |  |  |  | 0 | bar: WEEK 3 T
Hire electrician to wire tables at North location | Half Day |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Hire electrician to wire tables at Downtown | Half Day |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Milestone: Test Run
Hold test run with staff family and friends in order simulate full service |  |  |  | 0 | bar: WEEK 3 F
Collect feedback from test run and identify ways to improve or any problems |  |  |  | 1 | bar: WEEK 3 F
Implement feedback from test run |  |  |  | 3 | bar: WEEK 3 F to WEEK 4 T
Milestone: Launch
Schedule launch day |  |  |  | 0 | bar: WEEK 1 M
Prepare for launch day by coordinating and identifying outstanding needs of GMs |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Launch day |  |  |  | 0 | bar: WEEK 4 T
Milestone: Retrospective
Conduct Retrospective. What worked, what didn't? |  |  |  | 2 | bar: WEEK 5 T to WEEK 5 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Procurment
Work with GM @ North location location to identiy number of tablets needed. |  | 0 | 0 | 0 | 1 | H
Work with GM @ Downtown to identify number of tablets needed. |  | 0 | 0 | 0 | 1 | H
Determine if we will purchase and store backup tablets for emergencies |  | 0 | 0 | 0 | 1 | H
Assess available tablet options and specs from the supplier that meet requirements. |  | 1 | 1 | 1 | 2 | H
Create contract and statements of work for tablet vendor |  | 2 | 1 | 2 | 3 | H
Buy and receive the correct amount of tablets | Due to force majeure storm we need to wait(2 more weeks), or use an alternative supplier(5 days) | 10 | 7 | 10 | 14 | H
Milestone: Installation
Connect marketing team for branding and digital menu design |  | 0 | 0 | 0 | 1 | H
Work with tablet supplier to identify common issues and turn-around times resolving tablet problems. |  | 2 | 1 | 2 | 4 | H
Develop internal policy and troubleshooting guides for the tablet rollout and usage |  | 3 | 1 | 2 | 4 | M
Assess work required to ensure tablets integrate seamlessly with existing Hardware |  | 3 | 1 | 3 | 4 | L
Identify a location to store backup tablets |  | 0 | 0 | 0 | 1 | H
Identify bar section tables that need to be wired properly by electrician |  | 0 | 0 | 0 | 1 | H
Install one tablet to ensure proper installation and to identify any potential issues |  | 0 | 0 | 0 | 1 | M
Hire electrician to wire appropriate tables at Downtown location | Half Day | 3 | 2 | 3 | 4 | M
Hire electrician to wire appropriate tables at North location | Half Day | 3 | 2 | 3 | 4 | M
Add featured menu items and coupon values to tablets |  | 1 | 0 | 1 | 2 | M
Work with Carter on possible menu revamp |  | 10 | 4 | 10 | 14 | M
Milestone: Tablet Training
Develop a training program and rollout guide |  | 7 | 7 | 7 | 10 | H
Pre-training meeting to introduce tablets and changes |  | 1 | 1 | 1 | 2 | H
Cheif Tech will train GMs and key staff on tablets and end of shift security measures |  | 2 | 2 | 2 | 3 | H
Work with GMs to coordinate, schedule, and hold meetings to discuss rollout and report questions/concerns |  | 7 | 7 | 10 | 14 | L
Milestone: Test Run
Hold test run with staff family and friends in order simulate full service |  | 0 | 0 | 0 | 1 | H
Collect feedback from test run and identify ways to improve or any problems |  | 1 | 0 | 1 | 2 | M
Implement feedback from test run |  | 3 | 1 | 2 | 4 | L
Milestone: Launch
Schedule launch day |  | 0 | 0 | 0 | 1 | H
Prepare for launch day by coordinating and identifying outstanding needs of GMs |  | 2 | 1 | 2 | 4 | H
Launch day |  | 0 | 0 | 0 | 0 | H
Milestone: Retrospective
Conduct Retrospective. What worked, what didn't? |  | 2 | 2 | 2 | 3 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Online Project Plan: | https://docs.google.com/spreadsheets/d/1oQwYEMKILqX10N03fG8Ei1Saudgv_LBJ/edit?usp=sharing&ouid=113094715498170936423&rtpof=true&sd=true | 2022-10-10 | Project Plan within Project Planception

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction - faster, more efficient experience | Average ticket time for appetizers <8 minutes and <15 minutes for entrees. | Do we have enough back end/line cooks to accomodate a turn-around time of <eight minutes for appetizers and <15 minutes for entrees? | Assess order flow and fulfillment. Track time orders when they are served. We could use the new tablets to collect data points on time order and have our front end record time delivered. | FALSE
Customer Satisfaction - faster, more efficient experience | Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback. We could also use new tablets to record data points of payment processing time beginning and end. | FALSE
Customer Satisfaction - faster, more efficient experience | Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated or resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | FALSE
Customer Satisfaction - faster, more efficient experience | 95% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | FALSE
Customer Satisfaction - faster, more efficient experience | Average wait time of ten minutes or less before customers are seated | How can the wait time be reduced to under ten minutes? | Track wait times in the system to ensure customers are being seated in less than ten minutes. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average wait time of ten minutes or less before customers are seated | How can the wait time be reduced to under ten minutes? | Track wait times in the system to ensure customers are being seated in less than ten minutes. | Were you satisfied with your wait time today? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied
Average wait time of ten minutes or less before customers are seated | How can the wait time be reduced to under ten minutes? | Track wait times in the system to ensure customers are being seated in less than ten minutes. | How long did you have to wait before being seated today? | Multiple choice | 0-5 min | 5-10 min | 10-15min | 15 or more min
Average ticket time for appetizers <8 minutes and <15 minutes for entrees. | Do we have enough back end/line cooks to accomodate a turn-around time of <eight minutes for appetizers and <15 minutes for entrees? | Assess order flow and fulfillment. Track time orders when they are served. We could use the new tablets to collect data points on time order and have our front end record time delivered. | How long did it take for you to receive your appetizers? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Average ticket time for appetizers <8 minutes and <15 minutes for entrees. | Do we have enough back end/line cooks to accomodate a turn-around time of <eight minutes for appetizers and <15 minutes for entrees? | Assess order flow and fulfillment. Track time orders when they are served. We could use the new tablets to collect data points on time order and have our front end record time delivered. | How long did it take for you to receive your entrees? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback. We could also use new tablets to record data points of payment processing time beginning and end. | How long did it take you to complete the checkout process today? | Multiple choice | less than a minute | 1-3 minutes | more than 3 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback. We could also use new tablets to record data points of payment processing time beginning and end. | How satisfied are you using the tablet to checkout? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied
95% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you satisfied with your meal today? | Yes/No | Yes | No
95% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you able to order exactly what you wanted? If no, please explain. | Yes/No | Yes | No. Please explain:
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated or resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | Did you encounter any issues using the tablet? | Yes/No | Yes. Please explain: | No
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated or resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | How was your experience using the tablet to order your meal today? | Open-ended | Please explain: